## Dashboard
Crisis Management & Cross-Team Blocker Resolution Dashboard
|  | Status | Count
Team Members | 11 | Resolved | 3
Critical Incidents | 1 | Open | 0
Resolved Blockers | 3
On-Time Milestones % | 100
|  | Metric | Value
|  | Critical Incidents | 1
|  | Resolved Blockers | 3
|  | Open Risks | 2
|  | On-Time Milestones | 100

## Executive Summary
Project | Crisis Management & Cross-Team Blocker Resolution Framework
Mission | 10-Month Mars Rover Science Mission
Team Size | 11
Outcome | Critical blocker resolved; milestone protected

## Team Members
ID | Name | Role | Dept | Responsibility
TM01 | Shreya Dalvi | Science Lead | Science | Program Leadership
TM02 | Aryan Shah | Geology Lead | Science | Geological Analysis
TM03 | Riya Mehta | Astrobiology Lead | Science | Astrobiology
TM04 | Kunal Patel | Raman Specialist | Science | Spectroscopy
TM05 | Aditya Jain | Science Analyst | Science | Data Validation
TM06 | Neha Singh | Electronics Lead | Electronics | Sensors
TM07 | Vivek Rao | Embedded Engineer | Electronics | Controls
TM08 | Siddharth Gupta | Software Lead | Software | Software
TM09 | Priya Nair | Navigation Engineer | Software | Navigation
TM10 | Rahul Verma | Mechanical Lead | Mechanical | Drill System
TM11 | Ananya Kulkarni | Project Manager | Management | Coordination

## Stakeholders
ID | Stakeholder | Type | Influence | Interest
SH01 | Project Manager | Internal | High | High
SH02 | Science Team | Internal | High | High
SH03 | Faculty Mentor | External | High | Medium
SH04 | Competition Organizers | External | High | High
SH05 | Sponsors | External | Medium | Medium

## Milestones
Milestone | Month | Status
M1 | 1 | Completed
M2 | 2 | Completed
M3 | 3 | Completed
M4 | 4 | Completed
M5 | 5 | Completed
M6 | 6 | Planned
M7 | 7 | Planned
M8 | 8 | Planned
M9 | 9 | Planned
M10 | 10 | Planned

## Dependencies
ID | Dependent | Supporting | Dependency | Priority
DEP01 | Science | Mechanical | Drill Availability | Critical
DEP02 | Science | Electronics | Sensor Calibration | Critical
DEP03 | Science | Software | Data Acquisition | Critical

## Risk Register
Risk ID | Risk | Prob | Impact | Score | Mitigation
R001 | Drill Failure | High | High | 9 | Preventive Testing
R002 | Calibration Delay | Medium | High | 6 | Validation

## Issue Register
Issue ID | Issue | Owner | Status | Severity
I004 | Drill Torque Instability | Mechanical Lead | Open | Critical
I005 | Data Transfer Failure | Software Lead | Open | High

## RAID Log
Type | ID | Description | Status
Risk | R001 | Drill Failure | Mitigated
Issue | I004 | Torque Instability | Resolved
Dependency | DEP01 | Drill Availability | Managed

## Blocker Register
Blocker | Date | Description | Severity | Status
B001 | 2026-03-12 | Subsurface sampling blocked | Critical | Resolved

## Incident Log
Incident | Date | Blocker | Priority | Status
INC001 | 2026-03-12 | B001 | Critical | Closed

## Escalation Matrix
Severity | Escalate To | Response | Target
Critical | PM + Faculty Mentor | 1 Hour | 24 Hours

## Communication Log
Date | Sender | Recipient | Purpose
2026-03-12 | PM | Faculty Mentor | Escalation

## Impact Assessment
Criteria | Weight
Schedule Impact | 30%
Science Impact | 30%
Dependency Impact | 20%
Resource Impact | 10%
Stakeholder Impact | 10%

## Resolution Workflow
Step
Detection
Logging
Assessment
Escalation
War Room
Root Cause
Fix
Validation
Closure

## Case Study
Section | Details
Situation | Drill failed during mission month 6
Impact | 10-day delay risk
Resolution | Motor replacement and recalibration
Outcome | Resolved in 6 days

## KPI Dashboard Data
Metric | Value
Critical Incidents | 1
Resolved Blockers | 3
On-Time Milestones % | 100
Open Risks | 2